## LifecycleIssues
Type change | Type | ck | Key | Summary | Status | Resolution | Created | Updated | Affects Version/s
| Improvement | x | DDILIFE-3510 | FragmentInstances can not be properly validated | In Progress | Unresolved | 2015-09-10 | 2015-09-17 | 3.3_Beta
| Improvement | x | DDILIFE-3519 | Add Classification management based on Copenhagen Mapping | Resolved | Fixed | 2015-12-16 | 2016-03-10 | 3.3_Beta
| Improvement | x | DDILIFE-3524 | d:ConditionalText | In Progress | Unresolved | 2016-01-26 | 2016-03-31 | Future Versions, 3.3_Beta
| Improvement | x | DDILIFE-3533 | MeasureDefinition | In Progress | Unresolved | 2016-09-09 | 2016-09-28 | ask Guillaume about need in 3.3
Improvement | TechTask | x | DDILIFE-3178 | 444(Mantis): Consider use of formating other than XHTML in StructuredString | In Progress | Unresolved | 2011-02-06 | 2012-09-20 | Jeremy
Improvement | TechTask |  | DDILIFE-3180 | 359(Mantis): Abstraction of data source instead of should replace datacollection | Closed | Referred | 2010-04-26 | 2012-09-20 | Future Versions
| Bug | x | DDILIFE-3511 | Review function and documentation of In/Out Parameters and Binding | Open | Unresolved | 2015-12-14 | 2016-08-04 | 3.2
| Improvement | x | DDILIFE-3525 | displayLabel and secondary response domain in grids | Open | Unresolved | 2016-04-08 | 2016-08-04
| Improvement | x | DDILIFE-3526 | "Other, please specify" in QuestionGrid | Open | Unresolved | 2016-05-18 | 2016-08-04
| Improvement | x | DDILIFE-3528 | Measure in QuestionGrid | Open | Unresolved | 2016-07-04 | 2016-08-10 | 3.3_Beta
| Improvement | x | DDILIFE-3534 | Include documentation on DDI - CV availablity at the element/attribute level | Open | Unresolved | 2016-10-25 | 2016-10-25
Bug | TechTask | x | DDILIFE-3179 | 373(Mantis): (RDF) Support for other standardized identification schemes. | Open | Unresolved | 2010-05-02 | 2012-09-20
Improvement | TechTask | x | DDILIFE-2931 | 622(Mantis): Filter variable (missing indicator) and categorical variable for indication of different types of missing | Open | Unresolved | 2014-04-29 | 2014-04-29
Improvement | TechTask | x | DDILIFE-2932 | 620(Mantis): Integrity constraints for data values | Open | Unresolved | 2014-04-29 | 2014-04-29
Improvement | TechTask | x | DDILIFE-2933 | 619(Mantis): Constraints on data values: unique and not null | Open | Unresolved | 2014-04-29 | 2014-04-29
Improvement | TechTask | x | DDILIFE-2934 | 618(Mantis): Precision of measurement and others | Open | Unresolved | 2014-04-29 | 2014-04-29
Improvement | TechTask | x | DDILIFE-2935 | 617(Mantis): String range for text representation | Open | Unresolved | 2014-04-29 | 2014-04-29 | Larry will look at
Improvement | TechTask | x | DDILIFE-3026 | 601(Mantis): Need a Case Selection definition in Physical instance in order to go from physical to source data. | Open | Unresolved | 2013-05-25 | 2013-05-25
Improvement | TechTask | x | DDILIFE-3160 | 266(Mantis): Why are coverages (temporal¦ topical¦ spatial) identifiable when the parent is not? | Open | Unresolved | 2009-06-21 | 2012-09-20
Task | TechTask |  | DDILIFE-3161 | 364(Mantis): Why are modules are maintainable? | Closed | Won't do | 2010-04-27 | 2012-09-20
| Task |  | DDILIFE-2928 | 628(Mantis): Specific information on publication purpose of metadata items should be added | Closed | Won't do | 2014-07-09 | 2016-11-10 | 3.3
Improvement | TechTask | x | DDILIFE-3188 | 357(Mantis): Generalization of containers in datacollection | Reopened | Unresolved | 2010-04-25 | 2012-05-24 |  | assign to 3.3_Beta
Bug | TechTask | x | DDILIFE-3090 | 308(Mantis): Group/SubGroup Name mssing | Reopened | Unresolved | 2009-09-26 | 2012-09-20
Improvement | TechTask |  | DDILIFE-3035 | 515(Mantis): Need a means of cross referencing between structured strings in DDI documents | Reopened | Unresolved | 2012-06-21 | 2012-09-21
| Improvement | x | DDILIFE-3531 | Publication of individual items, Publication status CV? | Resolved | Fixed | 2016-08-11 | 2016-09-29
Improvement | TechTask | x | DDILIFE-2927 | 629(Mantis): Indicator missing for status of a metadata item | Resolved | Fixed | 2014-07-09 | 2014-07-09
Improvement | TechTask | x | DDILIFE-2929 | 627(Mantis): isPublished for every identifiable object | Resolved | Fixed | 2014-07-09 | 2016-09-29
Bug | TechTask | x | DDILIFE-2924 | 625(Mantis): Name¦ Label¦ and Description in ControlConstructType documentation wording error | Resolved | Unresolved | 2014-07-09 | 2014-09-25
Bug | TechTask | x | DDILIFE-2925 | 624(Mantis): Orphan element in reusable | Resolved | Unresolved | 2014-05-15 | 2014-09-25
Bug | TechTask | x | DDILIFE-3025 | 270(Mantis): ConceptReference has interative ConceptReference | Resolved | Unresolved | 2009-06-21 | 2013-07-31
Bug | TechTask | x | DDILIFE-3041 | 325(Mantis): URN Issues | Resolved | Unresolved | 2010-02-02 | 2012-09-21
Bug | TechTask | x | DDILIFE-3186 | 323(Mantis): URN of Identifiable Object | Resolved | Unresolved | 2010-01-04 | 2012-05-30
Improvement | TechTask | x | DDILIFE-2959 | 582(Mantis): XxxxReference should be simplified to Reference | Resolved | Unresolved | 2013-03-15 | 2013-12-28
Task | TechTask | x | DDILIFE-3134 | 520(Mantis): agency portion of DDIURNType restricts to a single '.' extension | Resolved | Unresolved | 2012-08-15 | 2016-10-03
Task | TechTask |  | DDILIFE-3187 | 443(Mantis): MultipleQuestionItemType is not documented | Closed | Done | 2011-02-04 | 2012-05-24
Task | TechTask |  | DDILIFE-3318 | 176(Mantis): Review for inclusion in 3.1 - holding bug for issues needing future review | Closed | Done | 2008-03-12 | 2009-01-13
Task | TechTask |  | DDILIFE-3185 | 514(Mantis): CLEAN UP following pulling content for documentation | Closed | Fixed | 2012-06-17 | 2012-06-17
Improvement | TechTask |  | DDILIFE-3157 | 362(Mantis): Logical filter variable | Closed | No fix required | 2010-04-26 | 2012-09-20
Improvement | TechTask |  | DDILIFE-3183 | 327(Mantis): default variable scheme for logical record | Closed | No fix required | 2010-02-05 | 2012-09-20
Improvement | TechTask |  | DDILIFE-3184 | 431(Mantis): Inconsistant pairing of schema name and module name | Closed | Won't do | 2010-11-04 | 2012-09-20
Bug | TechTask |  | DDILIFE-3054 | 248(Mantis): Legally possible to create 2 URNs or 2 ID sequences in all References | In Progress | Unresolved | 2009-02-24 | 2012-09-21
Improvement | TechTask |  | DDILIFE-3181 | 122(Mantis): CodeScheme Editing Requirements | In Progress | Unresolved | 2008-01-29 | 2012-09-20
Improvement | TechTask |  | DDILIFE-3182 | 189(Mantis): have all schemes inherit from an abstrct schemes | In Progress | Unresolved | 2008-03-20 | 2012-09-20
Improvement | TechTask |  | DDILIFE-2921 | 621(Mantis): xs:decimal should be replaced by xs:double | In Progress | Unresolved | 2014-04-29 | 2015-03-17 | 3.2
Improvement | TechTask |  | DDILIFE-3029 | 592(Mantis): Need to specify access restrictions down to a value of the variable representation | In Progress | Unresolved | 2013-04-04 | 2013-04-15 | Future
| Improvement |  | DDILIFE-3527 | Usability vs Reusability | Open | Unresolved | 2016-05-30 | 2016-05-30
| Improvement |  | DDILIFE-3532 | MeasurementUnit | Open | Unresolved | 2016-09-09 | 2016-09-28
Bug | TechTask |  | DDILIFE-3028 | 600(Mantis): Conflict between high level documents and field level content | Open | Unresolved | 2013-05-20 | 2015-03-26 | 3.2
Bug | TechTask |  | DDILIFE-3172 | 363(Mantis): ReferenceType allows two URNs | Open | Unresolved | 2010-04-26 | 2012-09-20
Improvement | TechTask |  | DDILIFE-3030 | 593(Mantis): Need to capture provenance down to the variable level | Open | Unresolved | 2013-04-04 | 2013-04-15 | Future
Improvement | TechTask |  | DDILIFE-3083 | 358(Mantis): Statistical indicators for test items | Open | Unresolved | 2010-04-26 | 2012-09-20 | Future
Task | TechTask |  | DDILIFE-2957 | 584(Mantis): reusable contains all Reference types requiring a change in reusable when changes occur elsewhere | Open | Unresolved | 2013-03-15 | 2013-12-28 | future Versions
Task | TechTask |  | DDILIFE-3055 | 504(Mantis): Change packaging module Group into a GroupScheme and change SubGroup to Group | Open | Unresolved | 2012-03-01 | 2012-09-21 | future Versions
| Bug |  | DDILIFE-3507 | InternationalStringType for Subject and Keyword | Resolved | Fixed | 2015-08-06 | 2016-01-14 |  | changed to Resolved
| Bug |  | DDILIFE-3529 | Reference can not represent concatenated unique ids using a . | Resolved | Fixed | 2016-07-25 | 2016-09-01 | 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3512 | Create a UnitType | Resolved | Fixed | 2015-12-16 | 2016-03-10 | 3.3_Beta | Wendy work required
| Improvement |  | DDILIFE-3513 | Add coverage information to Universe to align with GSIM | Resolved | Fixed | 2015-12-16 | 2016-05-04 | 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3514 | Add a concept reference to Group and StudyUnit | Resolved | Fixed | 2015-12-16 | 2016-01-07 | 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3515 | Add TypeOf Group/Study CV to Group and Study | Resolved | Fixed | 2015-12-16 | 2016-01-08 | 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3516 | Add a PhysicalInstanceGroup | Resolved | Fixed | 2015-12-16 | 2016-04-05 | 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3517 | Add CategorySchemeReference to ConceptualVariable | Resolved | Fixed | 2015-12-16 | 2016-03-10 | 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3518 | QuestionItems should link to RepresentedVariables | Resolved | Fixed | 2015-12-16 | 2016-09-08 | 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3521 | Not possible to group geographic locations | Resolved | Fixed | 2016-01-07 | 2016-04-21 |  | changed to Resolved
| Improvement |  | DDILIFE-3522 | DateTimeDomain: start and end dates | Resolved | Fixed | 2016-01-26 | 2016-02-04 | Future Versions, 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3523 | d:TypeOfComputationItem | Resolved | Fixed | 2016-01-26 | 2016-03-10 | Future Versions, 3.3_Beta | changed to Resolved
| Improvement |  | DDILIFE-3530 | Demand for generic grids | Resolved | Fixed | 2016-08-04 | 2016-09-08 |  | changed to Resolved
Bug | TechTask |  | DDILIFE-2930 | 626(Mantis): Duplication of Description field in SummaryItem and DisplayText | Resolved | Noted | 2014-07-09 | 2015-03-26
Task | TechTask |  | DDILIFE-2952 | 590(Mantis): General issues of circular dependencies¦ incorrect modularization...potential implementation costs | Resolved | Referred | 2013-03-15 | 2013-12-28 | future Versions

## USAGE
| NESSTAR | 2 | 2.1 | 2.5 | 3 | 3.1 | 3.2 | plan 4
| 5 | 1 | 0 | 11 | 0 | 1 | 9 | 3
Stats Can PUMF | 1
ANU | 1
IPUMS |  |  |  | 1
NHGIS |  |  |  | 1
ICPSR |  |  |  | 1
Roper |  |  |  | 1 |  |  | 1
DDA |  |  |  | 1 |  | 1
UKDA |  |  |  | 1 |  |  |  | 1
SERISS/DASISH | [6 empty] | 1
FSD |  | 1
MIDAS |  |  |  | 1 |  |  | 1
BLS | [6 empty] | 1
ISPS | [6 empty] | 1
Roper |  |  |  | 1 |  |  | 1 | 1
Scholars Portal | 1
STATSCAN - Microdata | 1 | [5 empty] | 1
NSD | 1
INSEE | [6 empty] | 1
ADISP |  |  |  | 1
GESIS |  |  |  | 1 |  |  | 1
IHSN |  |  |  | 1 |  |  |  | 1