## Sheet1
COGS Activity Plan [red=done; yellow=in process; green=ready to test] | Est Days | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Preparation work
1) List of XSD objects currently in use | 0.5 | bar: Day 1
2) Compare current CSV files to 3.3 XSD | 1 | bar: Day 2
3.3 to CSV
1) Defining mapping rules | 2
2) Columns and content capture all attributes | 2
3) Representation of choice in csv attributes | 1
4) Representation of substitution groups in csv attributes | 1
5) Documentation is present for all elements | 1
CV to UML
1) Content is same in both csv and UML | 2
2) What requries documentation (class, property, etc.) | 1
3) PIM content limited to published | 0-1
4) Conformance with Canonical XMI Standards | 1
High level documents
1) Definable group of contents which have supporting documentation | 2
Support for Examples
1) Associating examples with class level documentation | 0.5
2) Associating exmaples with defined content documentation | 1
CV to UML for DDI4
1) Content of XMI to CSV - without loss | 2 | bar: Day 5 to Day 6
2) What requries documentation (class, property, etc.) | 1 | bar: Day 7
4) Conformance with Canonical XMI Standards | 1 | bar: Day 8