## Sheet1
Carrying on with Drupal | Mitigation | Moving to COGS | Mitigation
Final Product is not what we want |  | Learing to use new environment / process (time &effort)
- Versioning | Add versioning capability to Drupal | No visualisation of editing | Develop visual interface
- Roll back | Roll back to last backup | Migration costs
- Diffs of change |  | Unknown whether XMI is correct | Verify XMI output. Investigate possibility to create other flavours
- Approvals | Use status flags in conjunction with build flag | Over reliance on one product
- Portability of platform | docker containers etc | Final product is not what we want | Investigate output compared to project goals, can we modify as needed
- consistency checking | on input validataion, reuse of objects, pick lists | Reliance on GitHub
- conformance | Develop business rule validation | - consistency checking | Develop of validation framework
- Systematic changes | Back end update | Unclear what conformance is | Develop business rule validation
- Maintainbility / skills | upgrade to v8. requires resources | Bulk changes | Specify a buk edit workflow
- Access to infrastructure (user management) | Appoint responsible person to manage accounts | - forking capabilities | Built in Git functionality
- Sandbox | Run multiple copies of drupal / local / cloud
- Flexibility of XMI | Multiple xmi writes / or do later in workflow
- difficulty to collaborate - cost of isolated changes | Run multiple copies of drupal / local / cloud
- Maintaining 2 production systems (Lifecycle / 4) | Have different sets of people?
- Output / result problem if we have 2 systems
- forking capabilities